## Sheet1
Task | Start Date | End Date | Duration (days) | Days to deadline | Status
Find out specification of components | 2023-01-16 | 2023-01-23 | 7 | -23 | DONE
Come up with HV & LV circuits | 2023-01-18 | 2023-02-06 | 19 | -9 | DONE
Test charging rate | 2023-01-23 | 2023-02-10 | 18 | -5 | PENDING
Test discharging rate | 2023-01-23 | 2023-02-10 | 18 | -5 | PENDING
Designing and fabrication power ports | 2023-01-30 | 2023-02-10 | 11 | -5 | IN PROGRESS
Speed test | 2023-01-19 | 2023-02-15 | 27 | 0 | PENDING
Braking test | 2023-01-20 | 2023-02-15 | 26 | 0 | PENDING
AC output voltage test of controller | 2023-01-19 | 2023-02-17 | 29 | 2 | PENDING
Navigation modes test | 2023-01-19 | 2023-02-17 | 29 | 2 | PENDING
Dashboard research & aquisition | 2023-02-06 | 2023-03-06 | 28 | 19 | IN PROGRESS
Mounting & wiring of components | 2023-03-06 | 2023-03-10 | 4 | 23 | PENDING
Formulas:
Days to deadline = [End Date]-TODAY()